## PA.5.0103 6.3
PA.5.0103/6.3: Tender for the conservation - restoration of two paintings belonging to Ta' Bernarda Chapel in Gharghur.
The tables that follow give the description of the rates (or unit prices) by using the relevant clauses of the Technical Specifications.
N.B. Three decimal points do not exist as currency; therefore such offers cannot be accepted. Offers are to be submitted up to two decimal points.
Item | Description | Unit | Technical Specifications | Rate Including Taxes, other Duties, and Discounts but Exclusive of VAT | Amount Including Taxes, Other Duties & Discounts but Exclusive of VAT
|  |  |  | € | €
BILL A
A | Conservation and restoration of two canvas paintings
Preamble
1.1 | Modifications to any part of the works needed for the proper completion and/or function of the works are to be authorised by the Consultant/Supervisor from the Contracting Authority. Such modifications may include additions, substitutions, omissions, changes in quality, form, kind, character, position, quantity, dimensions, level or line and changes in the specified sequence, method or timing of execution of the works. The contract may become invalid if no order for a modification is made. The technical expert from the Contracting Authority shall have the power to order any modifications to any part of the works necessary for the proper completion and/or functioning of the works. Such modifications may consist of additions, omissions, substitutions, changes in quality, quantity, form, character, kind, position, dimensions, level or line and changes in the specified sequence, method or timing of execution of the works. No order for a modificaiton may result in the invalidation of the contract. | LS |  | inc. | inc.
1.2 | Tenderer is to visit the areas where works are to be carried out and ensure that he/she fully understands the extent of works involved prior to submitting his offer. | LS |  | inc. | inc.
1.3 | All permits related to the execution of the works shall be the responsibility of the contractor. | LS |  | inc. | inc.
1.4 | The contractor will be responsible for site traffic management during the execution of which includes: proper barriers, signage, lighting as may be required and any expenses related to 'extra duty' police on site to ensure proper safety and traffic management on site. | LS |  | inc. | inc.
1.5 | Allow for preparing and updating when required, detailed method statement reports, Organisation and Methodology Report, Risk assessment and programme of work for both the paintings and decorative frames specified in this document for the approval of the Consultant/Supervisor in charge. | LS |  | inc. | inc.
1.6 | Allow for all insurances as required by the contract, in particular Article 13 of the Special Conditions. | LS |  | inc. | inc.
1.7 | All care shall be exercised to assure that no damage is made to any of the fabric during the process of works, including the buildings in question. | LS |  | inc. | inc.
1.8 | The Consultant/Supervisor or project manager in charge shall approve and direct all methods to be carried out. | LS |  | inc. | inc.
2 | Rates include working both by hand and for hoisting, lowering, transporting all material/equipment required. | LS |  | inc. | inc.
2.1 | Documentation and mapping are to be carried out prior to the commencement of works in order to understand the paintings' manufacturing techniques, state of conservation and any past interventions. | LS |  | inc. | inc.
2.2 | To print and erect a EU sign of dimensions 1 x1.2m at Ta Bernarda Chapel. Artwork will be provided by the Contracting Authority | LS |  | inc. | inc.
BILL B
B | Documentation/Detailed Organisation and Methodology Report
1.1 | Prior to the commencement of work, high resolution images of both the canvas paintings and decorative frames are to be submitted to and confirmed by the Contracting Authority. Photographic details of the paintings and decorative frames showing the manufacturing techniques which, incorporate, but is not limited to, possibly macro photography of the ground layer, canvas weave, brushstrokes, protective coating, etc. The state of conservation of both the paintings and decorative frames are to be documented in detail and by taking photographs (also possibly in graphic form such as AutoCAD). The photographic documentation also incorporates, but is not limited to, powdering, cupping, flaking, tenting, blistering, liftings of the paint layers; tears in the canvas support; biological deterioration; and past interventions. Following conservation and restoration intervention, high resolution, scaled images of both the entire paintings and their decorative frames and of close-up details are to be presented. |  |  |  | 0
Historical research and an in depth study of the paintings and their decorative frames will be carried out in order to obtain as much information about the paintings, artists and materials used. Further research will be carried out to achieve more information about the paintings' past interventions.
Rate also includes submitting all digital photographs taken before, during and after conservation/restoration and presented in a manner to show the conservation treatments carried out. The technical expert part of the Contracting Authority shall certify and sign all documentation. No certification of works will be affected unless this documentation is submitted to and confirmed by the conservator-restorer and/or project manager in charge. A detailed report on the treatments carried out on the canvas paintings and decorative frames including all data retrieved from documentation, and scientific investigations is to be produced. A thorough description and justification of the intervention methodology and materials used is to be included in the report. The report shall be compiled and endorsed by a conservator-restorer possessing a degree MQF level 6 or 7 in the conservation and restoration of canvas paintings.
B1.1a | Painting 1: The Assumption of the Virgin Mary | LS | Technical Specifications Sections B 7-12 and Section D | inc. | inc.
B1.1b | Painting 2: The Holy Trinity | LS | Technical Specifications Sections B 7-12 and Section D | inc. | inc.
BILL C
C | Restoration and Conservation treatment
C1 | Painting 1: The Assumption of the Virgin Mary | LS | Technical Specifications Section B 11 | inc. | inc.
C1.1 | Partial facing of the painting in-situ prior to transportation. Transportation of the painting including the gold decorative frame from the current location of the work of art to the conservation laboratory. |  |  |  | 0
C1.2 | Drawing up an in-depth Condition Assessment Report of the state of conservation and treatment proposal of the painting and decorative frame. |  |  |  | 0
C1.3 | Removal of the decorative frame and side wood from the auxiliary support. Removal of metal crowns. |  |  |  | 0
C1.4 | Cleaning the painting (front and verso) mechanically from superficial dirt and dust. |  |  |  | 0
C1.5 | Consolidation of liftings, flaking and cupping in the paint and preparatory layers. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C1.6 | Dismantling painting from the auxiliary frame. Disinfestation of the auxiliary frame with anoxia. |  |  |  | 0
C1.7 | Removal of facing and consolidation of liftings, flaking and cupping in the paint layer. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C1.8 | Cleaning the painting from the old varnish. Mechanical methods might need to be used to remove the paint splatters/drips from the surface of the painting. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C1.9 | Cleaning the verso of the painting and removal of deformations in the canvas support. |  |  |  | 0
C1.10 | Treating the painting from the verso including tear repair, applying a synthetic consolidant to adhere any further liftings in the paint and to protect the original canvas from any deformations that might occur during the lining process. |  |  |  | 0
C1.11 | Lining preparation and lining the painting on to a new compatible canvas (100% linen) using a synthetic adhesive. Canvas inlays where the original canvas is missing using 100% linen. |  |  |  | 0
C1.12 | Stretching the painting onto the original auxiliary frame or a new auxiliary support if necessary using Tulipwood, with bevelled edges, necessary crossbars and stainless steel expandable bolts. |  |  |  | 0
C1.13 | Infilling losses in the paint and preparatory layers using stucco (using gelatine and either calcium carbonate or hydrated gypsum). Levelling infilled lacunae and giving them a similar texture as the original paint layer. |  |  |  | 0
C1.14 | Retouching all losses in the paint layer that were previously infilled with stucco. Retouching using varnish colours/ watercolours and using the puntini/tratteggio technique. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C1.15 | Applying a synthetic varnish as a protective coating by spray. |  |  |  | 0
C1.16 | Consolidation and cleaning of the top gilded, wooden bar. (Treatments and materials to be approved by the project representative in charge). Infilling of losses (using gelatine and either calcium carbonate or hydrated gypsum) and gilding lacunae (integrated either using gold leaf or another stable material as used originally resembling the colour of gold). |  |  |  | 0
C1.17 | Reproduction of the three missing gilded, wooden bars including gilding (using gold leaf or another stable material as used originally resembling the colour of gold). |  |  |  | 0
C1.18 | Replacing the infested, deteriorated, wooden strips at the sides with new ones. |  |  |  | 0
C1.19 | Cleaning the metal crowns (these should not be reattached to the painting due to the fact that they are probably not the original crowns however they should be documented, conserved and placed next to the painting for viewing inside the chapel). |  |  |  | 0
C1.20 | Producing a final report which includes general and detailed photographs of the painting and decorative frame before, during and after the conservation and restoration process along with detailed, step by step, descriptions of the entire conservation/restoration project. |  |  |  | 0
C1.21 | Transportation to the desired location (probably to the Ta’ Bernarda Chapel if the restoration works inside the chapel are ready by the time of completion of the painting and decorative frame). |  |  |  | 0
C2 | Painting 2: The Holy Trinity | LS | Technical Specifications Section B 11 | inc. | inc.
C2.1 | Partial facing of the painting in-situ prior to transportation. Transportation of the painting including the gold decorative frame from the current location of the work of art to the conservation laboratory. |  |  |  | 0
C2.2 | Drawing up an in-depth Condition Assessment Report of the state of conservation and treatment proposal of the painting and decorative frame. |  |  |  | 0
C2.3 | Cleaning the painting (front and verso) mechanically from superficial dirt and dust. |  |  |  | 0
C2.4 | Consolidation of liftings, flaking and cupping in the paint and preparatory layers. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.5 | Dismantling painting from the auxiliary frame. |  |  |  | 0
C2.6 | Removal of facing and consolidation of liftings, flaking and cupping in the paint layer. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.7 | Cleaning the painting from the old varnish. Mechanical methods might need to be used to remove the paint splatters/drips from the surface of the painting. (Treatments and materials to be approved by the project manager in charge). |  |  |  | 0
C2.8 | Facing the painting prior to working on the verso. Removing the lining canvas and lining adhesive. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.9 | Treating the painting from the verso including tear repair, applying a synthetic consolidant to adhere any further liftings in the paint and to protect the original canvas from any deformations that might occur during the lining process. |  |  |  | 0
C2.10 | Lining preparation and lining the painting on to a new compatible canvas (100% linen) using a synthetic adhesive. Canvas inlays where the original canvas is missing using 100% linen. |  |  |  | 0
C2.11 | Stretching the painting onto a new auxiliary support using Tulipwood, with bevelled edges, necessary crossbars and stainless steel expandable bolts. |  |  |  | 0
C2.12 | Infilling losses in the paint and preparatory layers using stucco (using gelatine and either calcium carbonate or hydrated gypsum). Levelling infilled lacunae and giving them a similar texture as the original paint layer. |  |  |  | 0
C2.13 | Retouching all losses in the paint layer that were previously infilled with stucco. Retouching using varnish colours/ watercolours and using the puntini/tratteggio technique. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.14 | Applying a synthetic varnish as a protective coating by spray. |  |  |  | 0
C2.15 | Consolidation of liftings, flaking, cracks and detachments in the gilding and paint and preparatory layers. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.16 | Adhering any broken pieces of wood and reconstructing pieces where necessary. |  |  |  | 0
C2.17 | Cleaning the decorative frame from superficial dirt and grime. (Treatments and materials to be approved by the project representative in charge). |  |  |  | 0
C2.18 | Removal of rusted/broken hanging devices and rusted nails and replacing them with stainless steel devices. |  |  |  | 0
C2.19 | Infilling losses in the paint/gilding and preparatory layers using stucco (using gelatine and either calcium carbonate or hydrated gypsum). Levelling infilled lacunae and giving them a similar texture as the original paint layer. |  |  |  | 0
C2.20 | Retouching all losses in the paint layer that were previously infilled with stucco. Retouching mimetically using varnish colours / watercolours. Gilding lacunae where necessary. (Integrated either using gold leaf or another stable material as used originally resembling the colour of gold). |  |  |  | 0
C2.21 | Applying a synthetic varnish as a protective coating by spray. |  |  |  | 0
C2.22 | Producing a final report which includes general and detailed photographs of the painting and decorative frame before, during and after the conservation and restoration process along with detailed, step by step, descriptions of the entire conservation/restoration project. |  |  |  | 0
C2.23 | Transportation to the desired location (probably to the Ta’ Bernarda Chapel if the restoration works inside the chapel are ready by the time of completion of the painting and decorative frame). |  |  |  | 0
SUMMARY
A | Preamble | LS |  | incl. | incl.
B | Documentation/Detailed Organisation and Methodology Report | LS |  | 0 | 0
C1 | Painting 1: The Assumption of the Virgin Mary | LS | Technical Specifications Section B 12 | 0 | 0
C2 | Painting 2: The Holy Trinity | LS | Technical Specifications Section B 12 | 0 | 0
| GRAND TOTAL |  |  |  | 0